## Sheet1
| Josh | Mitch | Connor | Gabe | Jiangdi
Week 1 | Start collecting sounds to use, look into FMOD | Tutorial: finish with 2 to 3 more segments | Editor, Reactive | Custom events, Serialization | Finalize raycasting, finalize
| Finalize tutorial | Start next level segment (map) |  |  | using the binary map
Week 2 |  |  | Finalize basic editor | Impliment sound system, finalize all event systems | Help with editor and Lua scripts
Window: fullscreen on start, handle CTRL + Alt + DEL
minimization, ALT+TAB,
Week 3 |  |  | Editor: Scale, Rotate, Edit Values, and Delete
Week 4 | Audio Guide | Design Guide | Uninstall from start menu | Cheat Codes: god mode, skip to win, skip level
|  |  | Self-Play | Technical Design Guide