## Sheet1
| Josh | Mitch | Connor | Gabe | Jiangdi
Week 1 | Start collecting sounds to use | Tutorial: finish with 2 to 3 more segments | Editor, Reactive | Custom events, Serialization | Finalize raycasting, finalize
| Finalize tutorial, work on level design | Start next level segment (map) |  |  | using the binary map
FMOD Studio/FMOD sounds
Week 2 | Start work in engine | Finish prototype segment: Level 1 | Finalize basic editor | finalize collision events and grounded | Insert sound events for walking and
| find more sound assets | Start working in engine | Window: fullscreen on start, handle CTRL + Alt + DEL | Zilch/JSON | background music on start
| make UI assets (at least placeholder?) |  | minimization, ALT+TAB, | Cheat Codes: Reload Level shortcut, Load Next Level | start Audio Guide
| Start Art Guide |  | Editor: Camera, Reload, Terxture, Entities
Week 3 |  |  | Particle Effects
Week 4 | Polish and refine last minute issues | Design Guide | Uninstall from start menu | Cheat Codes: god mode, skip to win, skip level | Audio Guide
| Art Guide |  | Self-Play | Technical Design Guide