## Sheet1
| Josh | Mitch | Connor | Gabe | Jiangdi
Week 1 | Start collecting sounds to use | Tutorial: finish with 2 to 3 more segments | Editor, Reactive | Custom events, Serialization | Finalize raycasting, finalize
| Finalize tutorial, work on level design | Start next level segment (map) |  |  | using the binary map
FMOD Studio/FMOD sounds
Week 2 |  |  | Finalize basic editor | finalize collision events and grounded
|  |  | Window: fullscreen on start, handle CTRL + Alt + DEL | Zilch/JSON
minimization, ALT+TAB,
Week 3 |  |  | Editor: Camera, Reload, Terxture, Entities
Week 4 | Polish and refine last minute issues | Design Guide | Uninstall from start menu | Cheat Codes: god mode, skip to win, skip level | Audio Guide
|  |  | Self-Play | Technical Design Guide